## Start Here
Process-Improvement Checklist
A practical gate-by-gate checklist for selecting, analyzing, testing, and sustaining improvements.
bobbywalls.com ¦ Practical tools for building better business systems
How to use this workbook
1 | Use the Assessment sheet at the start of an improvement effort and again at key review points.
2 | Select Not started, In progress, Complete, or Not applicable for each item.
3 | Record evidence, decisions, or links in the Notes / evidence field.
4 | Create an Action Log entry for incomplete items that could block results or sustainability.
5 | Do not advance only because documents are complete. Confirm that the people doing the work understand and use the change.
Practical tips
• Treat this as a decision aid, not bureaucracy. Remove items that truly do not apply, but explain why.
• Prioritize customer impact, safety, quality, delivery, cost, and employee usability.
• No improvement is complete until ownership, standard work, measurement, and follow-up are established.
• Check for unintended consequences in downstream departments and with suppliers or customers.
LICENSE: © 2026 Bobby Walls. Personal/internal business use only. Not for resale, redistribution, client delivery, or rebranding.

## Assessment
Process-Improvement Checklist
Use the status dropdown and capture objective evidence for each checkpoint.
bobbywalls.com ¦ Practical tools for building better business systems
ID | Phase | Checkpoint | Why it matters | Status | Notes / evidence | Owner | Due date
01 | DEFINE | Customer / stakeholder need is clear | Prevents optimizing work that does not create needed value. | Not started
02 | DEFINE | Process boundaries, trigger, and output are defined | Avoids scope drift and conflicting maps. | Not started
03 | DEFINE | Process owner and improvement sponsor are named | Establishes decision rights and accountability. | Not started
04 | DEFINE | Problem statement uses facts, magnitude, and impact | Separates the problem from a preferred solution. | Not started
05 | DEFINE | Baseline measure and target are agreed | Creates a fair basis for evaluating improvement. | Not started
06 | UNDERSTAND | Frontline employees participated in mapping | Captures how work actually happens. | Not started
07 | UNDERSTAND | Current-state steps, decisions, handoffs, and delays are mapped | Makes friction and ownership visible. | Not started
08 | UNDERSTAND | Exceptions, rework loops, and workarounds are documented | Prevents designing only for the ideal case. | Not started
09 | UNDERSTAND | Data sources and measurement definitions are reliable | Avoids acting on inconsistent numbers. | Not started
10 | UNDERSTAND | Customer, employee, supplier, and downstream impacts are considered | Reduces local optimization. | Not started
11 | ANALYZE | Immediate risks are contained | Protects customers and operations while analysis continues. | Not started
12 | ANALYZE | Potential causes are based on evidence, not blame | Focuses action on controllable system conditions. | Not started
13 | ANALYZE | Root cause has been verified or is testable | Prevents expensive fixes aimed at symptoms. | Not started
14 | ANALYZE | Constraints and bottlenecks are identified | Targets the part of the system limiting performance. | Not started
15 | ANALYZE | Waste and non-value-added activity are identified | Creates options to simplify the flow. | Not started
16 | IMPROVE | Proposed change clearly addresses the cause | Links the solution to the analysis. | Not started
17 | IMPROVE | Expected benefit and effort are estimated | Supports practical prioritization. | Not started
18 | IMPROVE | Risks, controls, and rollback plan are documented | Makes experimentation safe. | Not started
19 | IMPROVE | A small-scale pilot and prediction are defined | Creates a learning test instead of a broad rollout. | Not started
20 | IMPROVE | Outcome and balancing measures are selected | Detects both benefit and unintended harm. | Not started
21 | IMPLEMENT | Roles and RACI assignments are clear | Prevents missed handoffs and duplicate work. | Not started
22 | IMPLEMENT | Standard work, forms, systems, and training are updated | Embeds the new method in daily operations. | Not started
23 | IMPLEMENT | Affected people understand the purpose and change | Improves adoption and surfaces usability issues. | Not started
24 | IMPLEMENT | Cutover timing and support are planned | Reduces disruption during transition. | Not started
25 | IMPLEMENT | Customers or suppliers are notified when needed | Protects external relationships. | Not started
26 | SUSTAIN | Results are compared with baseline and target | Confirms whether the change worked. | Not started
27 | SUSTAIN | Process owner reviews the KPI at a defined cadence | Creates ongoing control. | Not started
28 | SUSTAIN | Corrective triggers and response are defined | Prevents gradual performance drift. | Not started
29 | SUSTAIN | Audit or observation confirms the new method is used | Tests actual practice, not documentation alone. | Not started
30 | SUSTAIN | Lessons learned and next PDCA cycle are recorded | Builds organizational learning. | Not started

## Action Log
Improvement Action Log
Track follow-up actions created from the checklist.
bobbywalls.com ¦ Practical tools for building better business systems
Action ID | Related checklist ID | Action | Owner | Date opened | Due date | Priority | Status | Closure evidence
A-01
A-02
A-03
A-04
A-05
A-06
A-07
A-08
A-09
A-10
A-11
A-12
A-13
A-14
A-15
A-16
A-17
A-18
A-19
A-20
A-21
A-22
A-23
A-24
A-25